## Sprint 1 Backlog
Story # | Sprint Backlog Item | Task # | Volunteer | Task Details ( BY RAJAT KATARIA) | Initial Effort Estimate (hrs) | New Estimates of Effort remaining at end of | [5 empty] | Status
[6 empty] | Day1 | Day2 | Day3 | Day4 | Day5 | Day6
US001 | As a admission desk executive /pharmacist/ diagnostic center executive I want to be able to log in the hospital website with my user ID and password So that I carry out my transactions | Task 1 |  | Write a program for displaying the home page | 5 | New Estimates of Effort remaining at end of Day1: 4; New Estimates of Effort remaining at end of Day2: 4; New Estimates of Effort remaining at end of Day3: 0 | Closed
|  | Task 2 |  | Design the UI for the Home page | 4 | New Estimates of Effort remaining at end of Day1: 3; New Estimates of Effort remaining at end of Day2: 3; New Estimates of Effort remaining at end of Day3: 1 | In Progress
|  | Task 3 |  | Design and create the DB fields | 5 | New Estimates of Effort remaining at end of Day1: 3; New Estimates of Effort remaining at end of Day2: 4; New Estimates of Effort remaining at end of Day3: 2 | In Progress
|  | Task 4 |  | Write test conditions to test the home page | 3 | New Estimates of Effort remaining at end of Day1: 3; New Estimates of Effort remaining at end of Day2: 3; New Estimates of Effort remaining at end of Day3: 3 | Open
|  | Task 5 |  | ---- | 2 | New Estimates of Effort remaining at end of Day1: 2; New Estimates of Effort remaining at end of Day2: 2; New Estimates of Effort remaining at end of Day3: 2 | Open
|  | Task 6 | … | ---- | --
|  |  |  | Execute the tests | --
US002 | As a admission desk executive I want to be able to capture new patient information So that I can create a new patient in the system | Task 1 |  | ---- | 6 | New Estimates of Effort remaining at end of Day1: 6; New Estimates of Effort remaining at end of Day2: 6; New Estimates of Effort remaining at end of Day3: 6 | Open
|  | Task 2 |  | ---- | 5 | New Estimates of Effort remaining at end of Day1: 5; New Estimates of Effort remaining at end of Day2: 4; New Estimates of Effort remaining at end of Day3: 0 | Closed
|  | Task 3 |  | ---- | 5 | New Estimates of Effort remaining at end of Day1: 3; New Estimates of Effort remaining at end of Day2: 2; New Estimates of Effort remaining at end of Day3: 2 | In Progress
|  | Task 4 |  | ---- | 4 | New Estimates of Effort remaining at end of Day1: 2; New Estimates of Effort remaining at end of Day2: 0; New Estimates of Effort remaining at end of Day3: 0 | Closed
|  | Task 5 | … | ---- | --
Task 6
|  |  | … | ---- | --
US003 | As a admission desk executive I want to be able to edit existing patient information So that I can store the updated patient information in the system | Task 1 |  | ---- | 6 | New Estimates of Effort remaining at end of Day1: 6; New Estimates of Effort remaining at end of Day2: 6; New Estimates of Effort remaining at end of Day3: 6 | Open
|  | Task 2 |  | ---- | 5 | New Estimates of Effort remaining at end of Day1: 5; New Estimates of Effort remaining at end of Day2: 4; New Estimates of Effort remaining at end of Day3: 0 | Closed
|  | Task 3 |  | ---- | 5 | New Estimates of Effort remaining at end of Day1: 3; New Estimates of Effort remaining at end of Day2: 2; New Estimates of Effort remaining at end of Day3: 2 | In Progress
|  | Task 4 |  | ---- | 4 | New Estimates of Effort remaining at end of Day1: 2; New Estimates of Effort remaining at end of Day2: 0; New Estimates of Effort remaining at end of Day3: 0 | Closed
|  | Task 5 |  | ---- | --
Task 6
|  |  | … | ---- | --
US004 | As a admission desk executive I want to be able to delete existing patient from system | Task 1 |  | ---- | 6 | New Estimates of Effort remaining at end of Day1: 6; New Estimates of Effort remaining at end of Day2: 6; New Estimates of Effort remaining at end of Day3: 6 | Open
|  | Task 2 |  | ---- | 5 | New Estimates of Effort remaining at end of Day1: 5; New Estimates of Effort remaining at end of Day2: 4; New Estimates of Effort remaining at end of Day3: 0 | Closed
|  | Task 3 |  | ---- | 5 | New Estimates of Effort remaining at end of Day1: 3; New Estimates of Effort remaining at end of Day2: 2; New Estimates of Effort remaining at end of Day3: 2 | In Progress
|  | Task 4 |  | ---- | 4 | New Estimates of Effort remaining at end of Day1: 2; New Estimates of Effort remaining at end of Day2: 0; New Estimates of Effort remaining at end of Day3: 0 | Closed
|  | Task 5 | … | ---- | --
Task 6
|  |  | … | ---- | --
US005 | As a admission desk executive I want to be able to view all the active patients currently admitted in the hospital | Task 1 |  | ---- | 6 | New Estimates of Effort remaining at end of Day1: 6; New Estimates of Effort remaining at end of Day2: 6; New Estimates of Effort remaining at end of Day3: 6 | Open
|  | Task 2 |  | ---- | 5 | New Estimates of Effort remaining at end of Day1: 5; New Estimates of Effort remaining at end of Day2: 4; New Estimates of Effort remaining at end of Day3: 0 | Closed
|  | Task 3 |  | ---- | 5 | New Estimates of Effort remaining at end of Day1: 3; New Estimates of Effort remaining at end of Day2: 2; New Estimates of Effort remaining at end of Day3: 2 | In Progress
|  | Task 4 |  | ---- | 4 | New Estimates of Effort remaining at end of Day1: 2; New Estimates of Effort remaining at end of Day2: 0; New Estimates of Effort remaining at end of Day3: 0 | Closed
|  | Task 5 | … | ---- | --
Task 6
|  |  | … | ---- | --
US006 | As a admission desk executive I want to be able to search for a patient So that I am able to view the details | Task 1 |  | ---- | 6 | New Estimates of Effort remaining at end of Day1: 6; New Estimates of Effort remaining at end of Day2: 6; New Estimates of Effort remaining at end of Day3: 6 | Open
|  | Task 2 |  | ---- | 5 | New Estimates of Effort remaining at end of Day1: 5; New Estimates of Effort remaining at end of Day2: 4; New Estimates of Effort remaining at end of Day3: 0 | Closed
|  | Task 3 |  | ---- | 5 | New Estimates of Effort remaining at end of Day1: 3; New Estimates of Effort remaining at end of Day2: 2; New Estimates of Effort remaining at end of Day3: 2 | In Progress
|  | Task 4 |  | ---- | 4 | New Estimates of Effort remaining at end of Day1: 2; New Estimates of Effort remaining at end of Day2: 0; New Estimates of Effort remaining at end of Day3: 0 | Closed
Task 5
|  | Task 6 | … | ---- | --
|  |  | … | ---- | --
US007 | As a pharmacist I want to be able to capture the medicines issued to a patient So that I can issue new medicines for an existing patient | Task 1 |  | ---- | 6 | New Estimates of Effort remaining at end of Day1: 6; New Estimates of Effort remaining at end of Day2: 6; New Estimates of Effort remaining at end of Day3: 6 | Open
|  | Task 2 |  | ---- | 5 | New Estimates of Effort remaining at end of Day1: 5; New Estimates of Effort remaining at end of Day2: 4; New Estimates of Effort remaining at end of Day3: 0 | Closed
|  | Task 3 |  | ---- | 5 | New Estimates of Effort remaining at end of Day1: 3; New Estimates of Effort remaining at end of Day2: 2; New Estimates of Effort remaining at end of Day3: 2 | In Progress
|  | Task 4 |  | ---- | 4 | New Estimates of Effort remaining at end of Day1: 2; New Estimates of Effort remaining at end of Day2: 0; New Estimates of Effort remaining at end of Day3: 0 | Closed
Task 5
|  | Task 6 | … | ---- | --
|  |  | … | ---- | --
US008 | As a diagnostics executive I want to be able to capture the diagnostocs conducted to a patient So that I can add new tests for an existing patient | Task 1 |  | ---- | 6 | New Estimates of Effort remaining at end of Day1: 6; New Estimates of Effort remaining at end of Day2: 6; New Estimates of Effort remaining at end of Day3: 6 | Open
|  | Task 2 |  | ---- | 5 | New Estimates of Effort remaining at end of Day1: 5; New Estimates of Effort remaining at end of Day2: 4; New Estimates of Effort remaining at end of Day3: 0 | Closed
|  | Task 3 |  | ---- | 5 | New Estimates of Effort remaining at end of Day1: 3; New Estimates of Effort remaining at end of Day2: 2; New Estimates of Effort remaining at end of Day3: 2 | In Progress
|  | Task 4 |  | ---- | 4 | New Estimates of Effort remaining at end of Day1: 2; New Estimates of Effort remaining at end of Day2: 0; New Estimates of Effort remaining at end of Day3: 0 | Closed
Task 5
|  | Task 6 | … | ---- | --
|  |  | … | ---- | --
US009 | As a admission desk executive I want to be able to get existing patient information So that I can raise the bill for the patient | Task 1 |  | ---- | 6 | New Estimates of Effort remaining at end of Day1: 6; New Estimates of Effort remaining at end of Day2: 6; New Estimates of Effort remaining at end of Day3: 6 | Open
|  | Task 2 |  | ---- | 5 | New Estimates of Effort remaining at end of Day1: 5; New Estimates of Effort remaining at end of Day2: 4; New Estimates of Effort remaining at end of Day3: 0 | Closed
|  | Task 3 |  | ---- | 5 | New Estimates of Effort remaining at end of Day1: 3; New Estimates of Effort remaining at end of Day2: 2; New Estimates of Effort remaining at end of Day3: 2 | In Progress
|  | Task 4 |  | ---- | 4 | New Estimates of Effort remaining at end of Day1: 2; New Estimates of Effort remaining at end of Day2: 0; New Estimates of Effort remaining at end of Day3: 0 | Closed
|  | Task 5 | … | ---- | --
|  | Task 6 | … | ---- | --

## Sprint 1 Burndown Chart
Day0 | Day1 | Day2 | Day3 | Day4 | Day5 | Day6
300 | 260 | 220 | 160 | 90 | 65 | 0
300 | 250 | 200 | 150 | 100 | 50 | 0